## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | M-1 | 1.Choose the data (refer to Day 3 ppt) either small, medium or large text data. 2.Read the data file (either web scrap or import as csv or txt files) 3.Store the data in the database and fetch the data. 4. Do text cleaning(like removing unnecessary text like emojis) and Normalization (like lowercasing, tokenizing, lemmatizing , POS tagging) 5.Using multiprocessing techniques, find the word and its counts. | MUST HAVE |  | mentor | 3- Completed
2 | 2 | M-2 | 1. Sentiment analysis 2. Store in DB 3. Apply parallelism 4. Send the summary email | MUST HAVE |  | mentor | 3- Completed
3 | 3 | M-3 | 1.Load Dataset. 2.Sends each data text in parallel to an LLM or any unsupervised learning algorithm for sentiment classification/topic modelling/text classification. 3.Saves results into a CSV (or your text storage DB). 4. Mail the csv file. 5. Measure the accuracy and performance of output using traditional method / unsupervised learning method (measuring the output prediction time) | MUST HAVE |  | mentor | 3- Completed
4 | 4 | M-4 | Create an UI part for the project.(preferably using streamlit) | MUST HAVE |  | mentor | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 36 | 6 | 6 | 5 | 5 | 3 | 4 | 1 | 3 | 0 | 0 | 1 | 2 | 0 | 0
SPRINT BACKLOG
M-1 | M-1 | 1.Choose the data (refer to Day 3 ppt) either small, medium or large text data. 2.Read the data file (either web scrap or import as csv or txt files) 3.Store the data in the database and fetch the data. 4. Do text cleaning(like removing unnecessary text like emojis) and Normalization (like lowercasing, tokenizing, lemmatizing , POS tagging) 5.Using multiprocessing techniques, find the word and its counts. | 2025-09-08 | 2025-09-16 | KAVERI | coding | Completed | 8 | Day 2: 2; Day 4: 2; Day 6: 2; Day 8: 1; Day 11: 1
M-2 | M-2 | 1. Sentiment analysis 2. Store in DB 3. Apply parallelism 4. Send the summary email | 2025-09-24 | 2025-10-02 | KAVERI | coding | completed | 6 | Day 3: 1; Day 6: 1; Day 8: 2; Day 12: 2
M-3 | M-3 | 1.Load Dataset. 2.Sends each data text in parallel to an LLM or any unsupervised learning algorithm for sentiment classification/topic modelling/text classification. 3.Saves results into a CSV (or your text storage DB). 4. Mail the csv file. 5. Measure the accuracy and performance of output using traditional method / unsupervised learning method (measuring the output prediction time) | 2025-10-09 | 2025-10-14 | KAVERI | coding | completed | 10 | Day 1: 3; Day 2: 2; Day 3: 2; Day 4: 3
M-4 | M-4 | Create an UI part for the project.(preferably using streamlit) | 2025-10-17 | 2025-10-27 | KAVERI | coding | completed | 12 | Day 1: 3; Day 2: 2; Day 3: 2; Day 5: 3; Day 6: 1; Day 7: 1
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | DAY | Impediments | Action Taken
1 | 2025-09-08 | overview of the project | got a brief overview of the project
1 | 2025-09-09 | explained about Sequential processing and Parallel processing | applied sequencial and multi processingd techniques on sample texts
1 | 2025-09-10 | explained about different type of text types and how to store it in database | chosen Sqlite3 as database
1 | 2025-09-11 | explained about regular expressions. | learned the different type of patterns.
1 | 2025-09-15 | chosen a dataset and explained about text cleaning | learnt how to clean the text using libraries.
1 | 2025-09-16 | milestone one presentation | presented and found no mistakes
2 | 2025-09-24 | M2-start(2-step verification & password) | after the class I have tried to send the automatic mail using SMTP server
2 | 2025-09-26 | explained about Count Vectorizer and TF-IDF Vectorizer | applied these concepts on my dataset and foung top words and least words
2 | 2025-09-30 | exlained about the work that we need to do in M2 | started working on milestone 2 implementation on my dataset
2 | 2025-10-01 | M2-presentation | clarified some some my doubts
2 | 2025-10-03 | M2-presentation | presented my milestone-2 work
2 | 2025-10-04 | M2-presentation | I have already done on 3rd oct
3 | 2025-10-06 | explained what we need to do in M3 part1 | started working on it(LLM implementation)
3 | 2025-10-09 | explained about difference between traditional and modern methods for sentimental analysis | listened to the class
3 | 2025-10-10 | brief overview of milestone-3 work | started working on it
3 | 2025-10-13 | m3-presentation | clarified some some my doubts
3 | 2025-10-14 | m3-presentation | presented my presentation
3 | 2025-10-15 | m3-presentation | listened to the others presentations
3 | 2025-10-16 | m3-presentation | listened to the others presentations
4 | 2025-10-17 | explained about the milestone-4 work | started working on streamlit
4 | 2025-10-23 | explained about what are the things we need to add in the dashboard | clarified some some my doubts
4 | 2025-10-24 | m4-presentation | continued working on streamlit
4 | 2025-10-27 | m4-presentation | presented my milestone-4 work
4 | 2025-10-28 | explain about the things we need to add in 5 MIN PPT Presentation | figured out the things that I need to add in PPT
4 | 2025-10-30 | m4-presentation | made some changes to my UI part
4 | 2025-11-03 | PPT presentation | started making ppt presentation
4 | 2025-11-04 | PPT presentation | presented my PPT

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-09-08 | 2025-09-18 | KAVERI | 2025-09-09 | 2025-09-16 | no
2 | 2 | 2025-09-24 | 2025-10-04 | KAVERI | 2025-09-29 | 2025-09-04 | no
3 | 3 | 2025-10-06 | 2025-10-16 | KAVERI | 2025-10-08 | 2025-10-14 | no
4 | 4 | 2025-10-17 | 2025-10-31 | KAVERI | 2025-10-22 | 2025-10-29 | yes | adding some more improvements to my UI part to make simple and user friendly.